## Cover Page
Code Review & Test Defect Log
Template Revision History
| Version | Release Date | Modified By | Change Description | Approved By
| 1 |  |  | First Release
Purpose
The purpose of this template id to Document the systematic examination (peer review) of computer source code. It is intended to find and fix mistakes overlooked during development and thereby improving both the overall quality of software and the developers' skills. For additional information refer Template Guidelines.
Associated Process/Phase
Phase/s - "PMC" .

## Code Review &Test Defect Log
Code Review & Test Defect Log | [10 empty] | Code Review & Test Defect Log
Sl.No | Area (Ticket Name,Source code ref.) | Review item | Internal / External | Defect Category | Developer Name | Defect Description | Reviewer / Tester Name | Review Date | Severity | Priority | Defect Type | Defect Cause | Defect Origin Phase | Defect Detection Phase | Status | Iteration No. | Resolved By | Attachments | Fixed in Version | Resolved Date | Rework Effort | Verified By | Verified Date | Remarks
Running serial no. | Give details of the Release Name and Module/Ticket Number. | Provide the name of item under review e.g. the code file / object name/ Test Case Id etc. | Whether the defect is reported by internal team or client | Defect category based on the review/ testing conducted | Developer of the code/ object / enhancement that is under review | Description of the defect encountered. It should be brief however self explanatory | Name of the person reviewing | Date the review is conducted | Severity of the defect. Refer guidelines for definitions | Priority to fix the defect-e.g. very high in case of a show stopper | Provide Defect Type. Refer detailed guidelines | Provide defect cause as per the reviewer/developer's opinion. Refer detailed guidelines | Which phase the defect was originated. | Phase in which the defect is detected e.g. a requirements defect may get detected during testing phase | Current status of the defect | Iteration no. if the same defect has re-surfaced | Defect resolved by whom |  |  | Date defect was resolved | Effort required for resolving the defect | Defect resolution verified by whom | Verification date | Remarks if any
[13 empty] | Defect Cause | proiroity |  |  | Defect Cause
[12 empty] | Defect Type |  | High
[9 empty] | Fatal | Open |  |  |  | Medium
[9 empty] | Serious(Operation degraded) | Closed | Requirement | Missing | Communication Gap | Low |  |  | Communication Gap
[9 empty] | Minor (Inconvenient usage) | Hold | Design / Impact Analysis | Interface | Oversight |  |  |  | External Factor
[9 empty] | Cosmetic | In Progress | Coding | Program Logic | Understanding Error |  |  |  | Inadequate Review (Input/ Output)
[10 empty] | Not a Defect | Testing | Optimization/Performance | External Factor |  |  |  | Inadequate knowledge/ experience
[11 empty] | Delivery | Data | Inadequate knowledge/ experience |  |  |  | Insufficient Standards / Processes / Tools
[12 empty] | Standards | Inadequate technical skills |  |  |  | Inadequate technical skills
[12 empty] | Usability Errors | Not Applicable |  |  |  | Time Constraint / Inflexible Schedules
[12 empty] | Suggestion. | Insufficient Standards / Processes / Tools |  |  |  | Understanding Error
[12 empty] | Not Relevant/ Redundant/ error in supporting documents | Time Constraint / Inflexible Schedules |  |  |  | Oversight
[12 empty] | Clarity | Inadequate Review (Input/ Output) |  |  |  | Not Applicable
Cosmetic/ Presentation
|  | Oversight/Lack of Attention |  |  |  | Ambiguous/ Unclear requirements
|  | Inadequacy/Mismatch of Skills/Proficiency |  |  |  | Requirements Incorrect
|  | Inadequate Inputs/ Specifications |  |  |  | Missing Requirements
|  | Specification not Clear |  |  |  | Design Incorrect
|  | Inadequate training |  |  |  | Design Incomplete
|  | Lack of Communication |  |  |  | Boundary Condition
|  | Inadequate Communication |  |  |  | Exception Handling
|  | Insufficient standards |  |  |  | Memory Leak
|  | Process not being followed |  |  |  | Incorrect Initialization
|  | Inadequate Process |  |  |  | Logic
|  | Incorrect version |  |  |  | Syntax Error
|  | Innate/Inbuilt defects |  |  |  | Coding standards violation
Data error
User friendliness/GUI
Code redundancy/ Maintainability
Software Feature missing/Doesn’t work
Documentation
Copy and Paste Error
Standards (not followed)
Invalid Test case
Inadequate coverage in Test cases
Insufficient and ambiguous test cases
Invalid Bug
Setup/environment
Performance
Duplicate Test Case
Incorrect/Missing Pre-conditions
Test steps not detailed/completed
Duplicate defect
Note on K4: • Major: A defect, which will cause an observable product failure or departure from requirements. • Minor: A defect that will not cause a failure in execution of the product. • Fatal: A defect that will cause the system to crash or close abruptly or effect other applications.
Note on M4: Defect Type: For detailed understanding on Defect Type refer Guidelines Tab
Note on N4: Defect Cause: For detailed understanding on Defect Cause refer Guidelines Tab
Note on U4: Specify the version of source code or document in which the defect was fixed.

## Guidelines
Guidelines: Defect Type, Cause
General Guidelines
This template shall be used for documenting the Code Review & Testing defects. In case of AMS/IMS projects, tickets resolution that involves code changes shall be subject to code reviews (sampling basis in case the no. of such tickets is huge) and testing. The defects encountered in such reviews/ testing shall be documented in this template.
CAPA shall be planned on defects as per below guidelines: - In case of Development projects - CAPA to be planned for a project phase (e.g. Development Phase / Testing Phase) Or earlier if the no. of defects are significant. - In case of AMS/IMS projects, CAPA can be planned when # of defects reach the threshold of 15 Or once in a Quarter whichever is earlier.
Details of Defect Type
Description | Guidelines
Coding / Program Algorithm fault/Logical Error | Fail to initialize correctly/Variable Declaration Error (Improper declaration / usage of variables, Type mismatch error in source code);Failure to set a data item, loop variables, initialize pointers, failure to clear flags Precession fault in coding - E.g. mixed precession ,floating point conversation , etc. Typographical Error - Spelling / Grammar mistake in documents/source code Presentation Error - For e.g.., If the screen layout needs to be improved. Say alignments, color, fonts etc. which do not affect the requirement. Comments / Message Error - Inadequate/ incorrect/ misleading or missing comments/messages in the source code Error / Exception handling - Inappropriate error handling, No error handling at all. Wrong Algorithm: The entire logic in a method is wrong and cannot provide the desired functionality, Missing or Inadequate or irrelevant or ambiguous functionality in source code; Incorrect use of programming constructs;Bracnching too soon or too late Testing for the wrong condition Wrong Expression/Computational Error: An expression (in an assignment or method call) computes the wrong value. A Boolean expression was wrong. Objects or their names were confused. The wrong method, attribute, or variable was used. Improper computation of the formulae / improper business validations in code. Boundary Related errors: Boundary conditions not addressed/incorrect Calculation Error: Outdated constants, wrong parentheses, truncation, incorrect conversion from one Control Flow errors: Programs runs amok, stops, loop error If then else, multiple cases error: Wrong inequalities (e.g.,> instead of >=), Comparison sometimes yields wrong result Standards not followed - Standards not followed like improper exception handling, use of E & D Formats and project related design/requirements/coding standards Missing Code/Implementations - The code for the desired functionality is missing. Relevant/ Redundant Code - If the unit within a review item is irrelevant to the scope of the item or the unit within a review item is redundant. For e.g.., Unused Paragraphs, Variables and unreachable statements. An error due to error in supporting documents. Navigation Error - Navigation not coded correctly in source code Sequencing / Timing Error - Error due to incorrect/missing consideration to timeouts and improper/missing sequencing in source code. Optimization /Performance Error - Optimal usage is lacking ,Performance is not unto the mark, Optimization w.r.t programming language, Multiple calls to procedures to be replaced by fewer calls in the code.
Inadequate/sub-optimal/Incorrect/Ambiguous/Missing Design | Panels, messages, help being reviewed are in error. ( Their design/implementation will adversely affect usability of the product.) Missing Design/Documentation fault - Design features/approach missed/not documented in the design document and hence does not correspond to requirements. A certain requirement is covered nowhere in the design. Design docs or user manual is wrong Interface Capability. - The design of an interface is wrong, so that the interface does not provide the functionality that it must provide. Optimization Error - Design will adversely affect the product's performance.
Incorrect /Missing /Inadequate/Ambiguous Requirements | Wrong or inaccurate requirements Requirement needs additional inputs for to be complete Implicit/Explicit requirements are missed/not documented during requirement phase Requirement is not clear to the reviewer. Also includes ambiguous use of words – e.g. Like, such as, may be, could be, might etc.
Interface error | Interface Capability - The design of an interface is wrong, so that the interface does not provide the functionality that it must provide. Interface Specification -The specification of an interface is wrong, so that the parameters involved cannot transfer all of the information required for providing the intended functionality. This is a less fundamental variant of IC: Only parameters need be added. Interface Description - The description of an interface is incomplete, wrong, or misleading, the description of a variable or class attribute or data structure not correct. Interface Use - An interface was used wrongly, i.e., in such a way as to violate the interface specification. Internal or external to application interfacing error, Incorrect handling of passing parameters, Incorrect alignment, incorrect/misplaced fields/objects, un friendly window/screen positions
Data and Database (data boundaries/storage/population) | 1. Problems when passing data between routines: Parameter list variables out of order or missing, Data type errors, Aliases and shifting interpretations of the same areas of memory, Misunderstood data values, Failure to clean up data on exception-handling exit, Outdated copies of data, Related variables get out of synch, Local setting of global data, Global use of local variables, Wrong value from a table 2. Data Boundaries : Undermanaged null terminated strings, Read/Write past end of a data structure , or an element in it 3. Read outside the limits of a message buffer : Compiler padding to word boundaries, Compiler padding to word boundaries, Value stack under/overflow, 4. Messaging : Messages sent to wrong process or port, Failure to validate an incoming message, Lost or out of synch messages 5. Data storage corruption: Overwritten changes, Data entry not saved, Too much data for receiving process to handle, Overwriting a file after an error exit or user abort 6.Incorrect Data Population - Incorrect data population / update in database Database Error - Error in the database schema/Design
Others | Stress Fault - E.g. overflowing buffers, lack of bounds checking" Timing fault - Processes fail to synchronize; Events happen in the wrong order Throughput fault - Performance lower than required Recovery fault - Incorrect recovery after another failure e.g. incorrect restore from backups" Hardware fault/System Error - Hardware doesn't perform as expected", Hardware and Operating System related error, Memory leak Standards - Item under review does not comply with the project or the organization standards
Usability Errors | Panels, messages, help being reviewed are in error. Their design/implementation will adversely affect usability of the product.
Suggestion. | If the defect reported is a suggestion.
Details of Defect Causes
Description | Guidelines
Communication Gap | Communication Gap Something not communicated or some misleading information communicated.
External Factor | External factor - Limitations of Architecture : The bug is the result of the limitation in the architecture used for development. - Errors in base system : This is specifically applicable for Porting projects. - Inadequate system/application knowledge : Inadequate application/system knowledge. This could be when we do not have complete knowledge of The system being developed
Inadequate Review (Input/ Output) | Requirements not understood properly Insufficient time spent on analysis Work product not reviewed against the desired requirements Insufficient impact analysis (changes in the requirement during design/ coding/ review/ testing) E.g. At any stage, checking for the completeness and sanity of inputs/ outputs - for a better understanding
Inadequate knowledge/ experience | The software professional does not have adequate knowledge or experience . This could be because training not given, training not effective
Insufficient Standards / Processes / Tools | 1 Insufficient Standards 1.1 Coding standards not available 1.2 Standards for the various activities of the project insufficient 1.3 Standards not available for version of software that is in use 2 Insufficient Processes/ Tools 2.1 Procedures/ standards not identified 2.2 Incorrect procedures defined 2.3 Process handbooks not available 2.4 Inadequate methodologies (e.g. design / development) E.g. licensing issues, Non-availability of tools, Evolving processes
Inadequate technical skills | Technical skills required to perform the activity inadequate
Time Constraint / Inflexible Schedules | Inadequate planning/ tracking Incorrect estimation Known time constraint - inadequate risk management E.g. Client has imposed a fixed/ impractical timeline, high profile client, competitive market strategies
Understanding Error | Understanding Error Failure to understand the Requirement / Specification / Standards.
Oversight | Ignorance - Forgot something because did not know about it -Did something wrong, although knew how to do it right Typo Did something trivial wrong typing mistake For E.g.., if the author commits the error in spite of the standards documents, Checklists, Requirements and other inputs being properly conveyed.
Not Applicable | Not Applicable Applicable only for Suggestion defect category.
Details of Defect Severity
Fatal | Show Stoppers. System hangs because of the software.
Major | This is not a shop stopper. This may include inconsistent with the Functional Requirements or data rendered is inconsistent and user cannot proceed with successful test. (Operation degraded)
Minor | These error allows the functionality of the software with some work around. (Inconvenient usage)
Suggestion | Improve user interface

## References
Details of Defect Causes
Communication Gap
External Factor
Inadequate Review (Input/ Output)
Inadequate knowledge/ experience
Insufficient Standards / Processes / Tools
Inadequate technical skills
Time Constraint / Inflexible Schedules
Understanding Error
Oversight
Not Applicable
Defect Type
Coding / Program Algorithm fault/Logical Error
Inadequate/sub-optimal/Incorrect/Ambiguous/Missing Design
Incorrect /Missing /Inadequate/Ambiguous Requirements
Interface error
Data and Database (data boundaries/storage/population)
Others
Usability Errors
Suggestion.